## BoQ for Jashma Shir School
Bill of Quantity (BoQ) for Painting of school buildings & boundary wall, repairing of metallic roofing of school building, repairing of electricity wiring of school building and provision of furniture for school offices for Jushma-e-Shir Boys & Girls high school
Project Name : Painting of school buildings & boundary wall, repairing of metallic roofing of school building, repairing of electricity wiring of school building and provision of furniture for school offices for Jushma-e-Shir Boys & Girls high school
Location: Jashma-e-Shir area / Pul-e-Khumri district
Province: Baghlan
General Notes: 1. All materials, tools, equipment and workmanship shall be in accordance with the Engineering Standards, Materials Specifications, and approved submittals. 2. All main installations/system modifications will be approved and inspected by UNHCR/Government/Partner Engineer prior to its implementation. 3. All materials, tools, equipment and items used in the projects need to be inspected and approved by engineer in charge. Approval of items are linked to the approval of submittals which should be shared two weeks in advance of delivery to projects site, for each item. 3. Contractors shall maintain a copy of the current national and international Engineering Standards on-site at all times during the implementation. 4. The contractor should ensure that implementation of the project will not cause damage to adjacent buildings, utilities or other property. This requirement is particularly important during cutting, filling, leveling, casting of concrete and all projected related activities. 5. The cost shall include for purchase, delivery, installation, placing, workmanship and required activities to working order of each activity. 6. Payment will be made as per field measurement and actual work done at the site.
| Description of Activities | Unit | Quantity | Unit cost/AFN | Total cost AFN
1 | Painting works for all existing buildings and boundary wall of the school
Preliminary Remarks: Paint coating for all plaster on exterior and interior walls and ceilings (best quality plastic paint) consisting of a ground coat and a finishing coat of painting due to manufacturer’s codes. The finishing coat has to cover the ground coat completely. All new and old surfaces have to be dry, trowel, clean and free from dust and lose old paint surfaces. Joints between walls and ceiling cut by trowel, all required activities (required filling and required paint coating , complete job) . Inclusive all soffits of windows and doors, painting of small areas, cleaning if necessary, all scaffolding is to be calculated in the unit rate. Sample of pint and filling materials should be provided for approval and color with the choice of client.
Painting of two main building of the school
1.01 | Painting of Interior walls : With minimum two coats of oil paint for all interior wall surfaces. All old surfaces have to be troweled, clean and free from dust and loose old paint's surfaces, if after trowelling the old loose surfaces, it needs filling, it should be done. The color of oil paint should according the color of the current oil paint of the walls. The scaffolding should be included in the unit rate with all other related activities. | m² | 1070 |  | 0
1.02 | Painting of ceiling : with minimum two coats of 75 % plastic for all celling surfaces. All new and old surfaces have cleaned and free from dust and loose old paint's surfaces. Applying water-thin able emulsion paint, solvent-free, washable and capable of capillary. The scaffolding should be included in the unit rate with all other related activities | m² | 1010 |  | 0
1.03 | Painting of entire Exterior walls: with 100 % best quality washable paint in minimum of three coats at out side for exterior walls. Before starting painting, all new and old surfaces have to be dry, troweled, clean and free from dust and loose old paint's surfaces. Applying silicate-based or adequate paint coating on exterior walls, with high- quality of plastic paint and resistance, excellent hiding capacity and resistance against atmospheric acid-pollutants. The scaffolding should be included in unit rate. Painting color should be according standard of MoE. | m² | 575 |  | 0
1.04 | Painting of black boards of the classrooms: with 100 % best quality washable paint in minimum of three coats, with high- quality of paint which is used for black boards of classrooms, excellent hiding capacity and resistance against atmospheric acid-pollutants, for 8 classrooms in both school buildings, with all required activities | m² | 30 |  | 0
1.05 | Painting of GI hand rail : with minimum two coats of best quality oil pain for handrail of school building and latrines' block, prior to the painting, the surfaces of handrail have to be troweled, clean and free from rust, dust and loose old paint' surfaces, with all required activities, it should be mentioned that, this activity is calculated in meter length, the entire length of handrail is considered. Painting color according choice of client. | m | 22 |  | 0
Painting of the guard room
1.06 | Painting of Interior walls and ceiling : with minimum two coats of filling and three coats of painting for all interior wall and ceiling surfaces. All new and old surfaces have to be troweled, clean and free from dust and loose old paint surfaces . Applying water-thin able emulsion paint, for interior walls, solvent-free, washable and capable of capillary. 75% plastic paint should be used. The scaffolding should be included in the unit rate with all required activities. Painting color according choice of client. | m² | 48 |  | 0
1.07 | Painting of entire Exterior walls: with 100 % best quality washable paint in minimum of three coats at out side for exterior walls. Applying silicate-based or adequate paint coating on exterior walls, with high- quality of plastic paint and resistance, excellent hiding capacity and resistance against atmospheric acid-pollutants. The scaffolding should be included in unit rate. Painting color according choice of client. | m² | 72 |  | 0
Painting of latrines' block and water reservoir
1.08 | Painting of entire Exterior walls: with 100 % best quality washable paint in minimum of three coats at out side for exterior walls of latrines' block and water reservoir. Applying silicate-based or adequate paint coating on exterior walls, with high- quality of plastic paint and resistance, excellent hiding capacity and resistance against atmospheric acid-pollutants, all new and old surfaces have to be dry, troweled, clean and free from dust and old paint loose surfaces with all required activities. The scaffolding should be included in unit rate. Painting color according choice of client. | m² | 120 |  | 0
Painting of boundary wall
1.09 | Painting of entire boundary wall: with 100 % best quality washable paint in minimum of three coats at both sides and top of boundary wall. Applying silicate-based or adequate paint coating on exterior walls, with high- quality of plastic paint and resistance, excellent hiding capacity and resistance against atmospheric acid-pollutants. Before painting, all new and old surfaces have to be dry, troweled, clean and free from dust and old paint loose surfaces with all required activities. The scaffolding should be included in unit rate. Painting color according choice of client. | m² | 2850 |  | 0
1.1 | Plastering of the damaged parts of school building 1:4, The damaged plastering parts of the school building (inside & outside) should be repaired with sand- cement plastering by 1:4, with all required activities. | m² | 20 |  | 0
| Sub-Total for painting works of all existing buildings and boundary wall of the school |  |  |  | 0
2 | Supply and installation of electricity ceiling fans & repairing of damaged part of electricity wiring
2.01 | Repairing of damaged electricity wiring of school, repairing the wiring for lights and fans which is done in PVC conduit / channel, the electricity wire should be 1x2.5mm², NYY type, Aflak, made in Iran with required activities. | m | 400 |  | 0
2.02 | Repairing of damaged conduit/ channel of electricity wiring , replacing the damaged conduits/channel which are used for the wiring of lights and fans on the surfaces of the walls and ceiling, by the size of 16mm x 25mm with required activities. | m | 240 |  | 0
2.03 | Repairing of damaged conduit/ channel of electricity wiring , replacing the damaged conduits/channel which are used for the wiring of lights and fans on the surfaces of the walls and ceiling, by the size of 25mm x 38 mm with required activities. | m | 120 |  | 0
2.04 | Switch (6 A) 220 V, 50Hz for lights including installation of switch plastic box and fixing in to the wall, good quality, with all required activities. | pcs | 32 |  | 0
2.05 | Sockets (10 A) 220 V, 50Hz under plaster type, for each class room 4 sockets and administration rooms 3 sockets should be considered, the socket should be under plaster type and will be screwed in the pvc under plaster box. The quality should be local standard. | pcs | 20 |  | 0
2.06 | Supply and installation of fluorescent tube lights which contains 2x36 Watt, 220V, 50Hz lamps length=120cm shall be fixed in the ceiling, including installation and screwing in ceiling and two lamps for each shall be considered. Asian standard quality or according the choice of the client. | pcs | 10 |  | 0
2.07 | Supply and installation of Circular lights which contains 36 Watt, 220V, 50Hz lamps for corridors and stock of the school building, size dia=30cm. Asian Standard Quality or according the choice of the client. | pcs | 4 |  | 0
2.08 | Supply and installation of electricity ceiling fan ( 56 inch) for classrooms and administration offices of the school, best quality fans, having copper motors with accessories and required items including provision and installation switches, complete to working order and subject to the approval of engineer in charge. | Unit | 20 |  | 0
2.09 | Circuit breakers (10 A, Zceck) automatic type, Supply and installation of Circuit breaker for power (20 A, Zceck) based on the design and specification with all required activities. | pcs | 12 |  | 0
2.1 | Circuit breakers (30 A, Zceck) automatic type, Supply and installation of Circuit breaker for power (30 A, Zceck) based on the design and specification with all required activities. | pcs | 2 |  | 0
2.11 | Circuit breaker (63 A, Zceck) three phase, Supply and installation of Circuit breaker for power (63 A, Zceck) three phase based on the design and specification with all required activities. | pcs | 2 |  | 0
2.12 | Checking the entire electricity wiring system of the building, after the repairing the electricity wiring system and installation of the electricity fixtures in the school building, the entire electricity system should be cheeked if there is a problem, it should be resolved and the system should be activated, all required materials and activities are included. | system | 1 |  | 0
2.13 | 5x10 mm2 Cable for connection from the source to the building including placing 80cm under the ground inside 50mm pvc pipe covered with 20cm sand and sign tape. Excavation of the ground placing the pipe and cable and backfilling is included in the price and inside the building it should be installed in the required PVC conduit / channel, The cable type should be NYY or comparable quality. | m | 130 |  | 0
2.14 | Electricity cable for installation of electricity meter: electricity cable 4x10mm² (copper) NYY, made in Iran, for installation of electricity meter for school on the pillar of public power | m | 8 |  | 0
2.15 | Supply and installation of electricity meter: Supply and installation of one phase electricity meter (Luna) Turkish, including supply and installation of circuit breaker (30 A, Zceck) automatic type, on the pillar of the public electricity power, complete job. | Unit | 1 |  | 0
2.16 | Supply and installation of meter box: Supply and installation of fabricated metallic box for electricity meter (30cm X 45cm) made in China, on the main pillar of the public electricity power system. | No | 1 |  | 0
2.17 | Transportation cost of community representative for execution of official governmental processes for installation of electricity meter. | LS | 1 |  | 0
| Sub-Total for Supply and installation of electricity ceiling fans & repairing of damaged part of electricity wiring |  |  |  | 0
3 | Repairing of damaged GI sheet of metallic roofing of school building
3.01 | Repairing of damaged GI sheets of metallic roofing of school building , The GI sheets of the metallic roofing of the school building which are damaged by light and heavy bullets during the armed clash in the area shuld be removed and properly replaced with new GI sheets, gauge 24 (made in Qazaqistan) with all required activities. | m² | 40 |  | 0
| Sub-Total for Repairing of damaged GI sheets of metallic roofing of school building |  |  |  | 0
4.01 | Provision and supply of furniture for principal, headmaster and teachers' offices of the school
4.01 | Provision and supply of one set sofa / couch, local made, good quality medium grade for seven persons including tables for principle and headmaster offices, prior to procurement and supply to the site the sample should be approved by in charge responsible. | Set | 2 |  | 0
4.02 | Provision and supply of table (140cm x70cmx75cm) for principle of the school, made in Turkish, prior to procurement and supply to the site the sample should be approved by in charge responsible. | No | 1 |  | 0
4.03 | Provision and supply of chair (rational) for principle of the school, prior to procurement and supply to the site the sample should be approved by in charge responsible. | No | 1 |  | 0
4.04 | Provision and supply of table (140cm x60cmx75cm) local made from best quality plywood, having drawers at both sides, for headmaster of the school, prior to procurement and supply to the site the sample should be approved by in charge responsible. | No | 1 |  | 0
4.05 | Provision and supply of chair ( ثابت بازو دار نکلی خارجی )for headmaster of the school, foreign made, prior to procurement and supply to the site the sample should be approved by in charge responsible. | No | 1 |  | 0
4.06 | Provision and supply of table (140cm x60cmx75cm) local made from best quality plywood, having drawers at both sides, for headmaster of the school, Turkish, prior to procurement and supply to the site the sample should be approved by in charge responsible. | No | 6 |  | 0
4.07 | Provision and supply of chair (Sabet ثابت بازو دار ) for teachers, local made in Kabul best quality, prior to procurement and supply to the site the sample should be approved by in charge responsible. | No | 20 |  | 0
4.08 | Provision and supply of files' shelves (120cm x40cmx190cm) local made from best quality plywood, having 3 panels with 4mm glasses and three panels with plywood at bottom , for principle and headmaster offices, prior to procurement and supply to the site the sample should be approved by in charge responsible. | No | 4 |  | 0
| Sub-Total Provision and supply of furniture for principal, headmaster and teachers' offices of the school |  |  |  | 0
5 | Supply and installation of fire extinguishers
5.01 | Supply and installation of fire extinguishers type dry chemical ABC 20Ib (9.07Kg) for extinguishing wood, plastic, oil, Fires involving ELECTRICAL APPARATUS and Cooking OIL & FAT etc, including wall bracket and wooden (Dried Russian wood, th=3cm) cabinet painted with red color with all required activities. | pcs | 4 |  | 0
| Sub-Total for Supply and installation of fire extinguishers |  |  |  | 0
6 | Provision and Supply of PVC Trash Bins for collection of garbage
6.01 | Provision and Supply of movable PVC Trash Bins ( 2 wheeled category) , h=94cm, dia=45cm, product of DELTA INTEGRATED INDUSTRIES, prior to provision and supply, approval of sample is a must. | No | 4 |  | 0
| Sub- Total for Provision and Supply of Trash Bins for collection of garbage |  |  |  | 0
7 | Supply and installation of metallic and stone signboards for the project
7.01 | Installation of Metal Signboard at construction site: supplying and installation of one steel board size 100x200cm, the frame made be made by 40x40x2 mm profile and covered with 1mm thick steel plate, Including GI steel poles dia = 3icn, th=3mm, excavation and concrete foundations. The description of the project will written in English and Dari, the board will be installed before starting of the work, Design will be given and handed over before starting. | LS | 1 | 0 | 0
7.02 | Installation of marble stone signboard : Supplying and installation of one signboard size 60x120cm, th= 3cm,made of marble stone on beside the entrance door wall in main building. The description of the project should be written in English and Dari. The board will be installed before handing over of the project. the design of signboard will be given before the handing over. | LS | 1 | 0 | 0
7.03 | Installation of Metal Signboard above the main entrance of the school compound: supplying and installation of one steel board size 3.5m x0.8m, the frame made by 40x40x2 mm profile and covered with 1mm thick steel plate, Including metallic pipes dia = 4icn, h= 4.5m th=2.5mm, including the required excavation and PCC concrete for foundations for installation of poles of signboard. In the signboard the name of school should be written. The board will be installed before handing over of the project. the design of signboard will be given before the handing over. | LS | 1 | 0 | 0
| Sub-Total for Supply and installation of metallic and stone signboards for the project |  |  |  | 0
Summary of BoQ
No | Items' description | Project cost per activity in AFN |  |  | Cost in USD
1 | Sub-Total for painting works of all existing buildings and boundary wall of the school | 0 |  |  | 0
2 | Sub-Total for Supply and installation of electricity ceiling fans and repairing of damaged part of electricity wiring | 0 |  |  | 0
3 | Sub-Total for Repairing of damaged GI sheets of metallic roofing of school building | 0 |  |  | 0
4 | Sub-Total Provision and supply of furniture for principal, headmaster and teachers' offices of the school | 0 |  |  | 0
5 | Sub-Total for Supply and installation of fire extinguishers | 0 |  |  | 0
6 | Sub- Total for Provision and Supply of Trash Bins for collection of garbage | 0 |  |  | 0
7 | Sub-Total for Supply and installation of metallic and stone signboards for the project | 0 |  |  | 0
| Grand-Total | 0 |  |  | 0